## Overview (hidden)
[7 empty] | Focus Area | #REF! |  | Slow down hackers |  | #REF! |  | #REF! |  | Increase Detection |  | Increase Detection |  | Increase Detection |  | Increase Detection |  | Reduce Damage |  | Reduce Damage |  | Reduce Damage |  | Reduce Damage |  | Reduce Damage |  | Streamline Compliance |  | Streamline Compliance |  |  | Streamline Compliance |  |  | Build Security Organization / Skills |  | Build Security Organization / Skills |  | Build Security Organization / Skills
IT Security Initiative | [7 empty] | #REF! |  | M252 | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF! | 0 | #REF! | 0
Progress KPI Reporting 2021 | [7 empty] | #REF! |  | # cyber security defences 1 | #REF! | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  | #REF! |  |  | #REF! |  |  | #REF! |  | #REF! | 1 | #REF! | 1
as of 04.09.2020 | [7 empty] | #REF! | #REF! | 6 | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Board Members | H Ressort | ITC Mapping |  | Group Iso Function | OEs ID | CIM ID | OE | #REF! | #REF! | Target 30.06.21 | Actuals 19.03.21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
.
Bäte | H1 CEO | 1 | Allianz SE, Allianz Europe | Shared Services | 1 | AZSE | Allianz SE | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 1 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Thallinger | H3 Investments Management | 2 | Allianz Investment | Shared Services | 2 | ADEUS | ADEUS Aktienregister-Service-GmbH | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Europe 3 | 3 | AGL | Allianz Global Life | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Shared Services | 4 | AIM | Allianz Investment Management (AIM) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Shared Services | 5 | ARE | Allianz Real Estate (ARE) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | Shared Services | 6 | IDS | Investment Data Services (IDS) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 5 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Mascher | H4 Operations | 3 | Allianz Technology | AZ Technology | 7 | AMOS | Allianz Technology | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 1 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Balbinot | H5 Insurance Western & Southern Europe, AZAP | 4 | AZAP | AZAP | 8 | CNPC | Allianz China - P&C | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 9 | CNH | Allianz China - Holding | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 10 | ID | Allianz Indonesia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 11 | JPLH | Allianz Japan - Life | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 12 | LAPC | Allianz Laos | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 13 | MY | Allianz Malaysia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 14 | PH | Allianz Philippine - L&H | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 15 | LK | Allianz Sri Lanka | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 16 | AS | Allianz Singapore | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 17 | TWL | Allianz Taiwan - Life | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 18 | TH | Allianz Thailand | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | AZAP | 19 | FIN | FinOS - Holding | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
| H2 Finance, Controlling, Risk | 5 | Allianz Benelux | Europe 2 | 21 | BLX | Allianz Benelux | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 6 | Allianz France | Europe 2 | 22 | FR | Allianz France | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 7 | Allianz Greece | Europe 3 | 23 | GR | Allianz Greece | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 8 | Allianz Italy | Europe 3 | 24 | IT | Allianz Italy | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 9 | Allianz Turkey | Europe 3 | 25 | TR | Allianz Turkey | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 17 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Theis | H7 Insurance German Speaking Countries & CEE | 10 | Allianz Germany | Europe 1 | 26 | AZD | Allianz Germany | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 11 | CEE | CEE | 27 | AT | Allianz Austria (Elementar) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 28 | BG | Allianz Bulgaria | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 29 | CZ | Allianz Czechia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 30 | HU | Allianz Hungary | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 31 | HR | Allianz Croatia (Zagreb) | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 32 | PL | Allianz Poland | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 33 | RO | Allianz Romania (Tiriac) | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 34 | RU | Allianz Russia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 35 | SK | Allianz Slovakia | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  | CEE | 36 | UKR | Allianz Ukraine | [10 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 11 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
| H2 Finance, Controlling, Risk | 12 | Allianz Suisse | Europe 1 | 37 | CH | Allianz Switzerland | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Hunt | H8 Asset Management, USA Life Insurance | 13 | Allianz Asset Management Holding (AAM) | Asset & Overseas | 38 | AAM | Allianz Asset Management Holding (AAM) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 15 | Allianz Global Investors (AGI) | Asset & Overseas | 39 | AGI | Allianz Global Investors (AGI) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 16 | Pacific Invest.Manag. Comp.(PIMCO) | Asset & Overseas | 40 | PIMCO | Pacific Investement Management Company (PIMCO) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
| H2 Finance, Controlling, Risk | 17 | Allianz Life | Asset & Overseas | 41 | USL | Allianz Life US | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 4 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [16 empty] | 0 |  |  | 0 |  |  | #REF! | #REF!
. | [17 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
Peiris | H9 Global Lines & Anglo Markets, MENA, Africa | 18 | Allianz Africa | AZ Africa | 42 | AFR | Allianz Africa | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | AZ Africa | 43 | MA | Allianz Morocco | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 2 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 19 | MENA | MENA | 44 | EGLH | Allianz Egypt L&H | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | MENA | 45 | EGPC | Allianz Egypt P&C | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | MENA | 46 | LB | Allianz Lebanon | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | MENA | 47 | SA | Allianz Saudi Arabia | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 4 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 20 | Allianz Global Corporate & Specialty (AGCS) | Europe 1 | 48 | AGCS | Allianz Global Corporate & Specialty (AGCS) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 21 | Reinsurance | Europe 1 | 49 | AZRE | Allianz Reinsurance | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 22 | Allianz Australia | Asset & Overseas | 50 | AU | Allianz Australia | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 23 | Allianz Ireland | Europe 3 | 51 | IE | Allianz Ireland | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 24 | Allianz UK | Europe 3 | 52 | UK | Allianz UK | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 25 | Euler Hermes Group | Europe 2 | 53 | EH | Euler Hermes | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
. |  |  |  |  | ∑ | ∑ | 12 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
.
de la Sota | H10 Business Transformation | 26 | Allianz Ibero & Latin America | IbertoLatAm | 54 | AR | Allianz Argentina | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 55 | BR | Allianz Brazil | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 56 | CO | Allianz Colombia | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 57 | MX | Allianz Mexico | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 58 | PT | Allianz Portugal | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  |  |  | IbertoLatAm | 59 | ES | Allianz Spain (Seguros) | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 6 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 27 | Allianz Partners | Europe 2 | 60 | AWP | Allianz Partners | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
|  | 28 | tbd | Shared Services | 60 | AZX | AllianzX | n.a. | n.a. | [8 empty] | n.a. | n.a. | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 8 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
[5 empty] | ∑ | ∑ | 60 | #REF! | #REF! | [8 empty] | #REF! | #REF! | #REF! | #REF! | [22 empty] | #REF! | #REF!
To be discussed: brauche wir die Übersicht-Seite. M.E. nicht unbedingt.

## Plan view
IT Security Investment Initiative
Progress KPI plan view
Focus Area | # | Measure | Progress KPIs | Baseline 01.01.2021 | Actuals 19.03.21 | Target 30.06.2021 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021
| KPI(1) | M252 | # cyber security defences 1 | 0 | 2 | 6 | 2 | 3 | 4 | 6
| KPI (2) | M253 | # cyber security defences 2 | 0 | 0 | 6 | 1 | 2 | 3 | 6
| KPI (3) | M254 | # cyber security defences 3 | 0 | 0 | 20 | 0 | 10 | 20 | 20
| KPI (4) | M255 | # cyber security defences 4 | 0 | 350 | 10000 | 1500 | 4000 | 6000 | 10000
| KPI (5) | M256 | # cyber security defences 5 | 0 | 0 | 5 | 1 | 2 | 4 | 5
| KPI (6) | M257 | # cyber security defences 6 | 0 | 3 | 12 | 3 | 4 | 8 | 12
| KPI (7) | M258 | # cyber security defences 7 | 0 | 3 | 20 | 3 | 6 | 12 | 20
2. Increase detection | KPI (8) | M259 | # cyber security defences 8 | 0 | 0 | 6 | 0 | 2 | 4 | 6
| KPI (9) | M260 | # cyber security defences 9 | 0 | 6 | 16 | 5 | 8 | 10 | 16
| KPI (10) | M261 | # cyber security defences 10 | 0 | 0 | 7 | 0 | 2 | 5 | 7
| KPI (11) | M262 | # cyber security defences 11 | 0 | 6 | 40 | 10 | 18 | 28 | 40
3. Reduce damage | KPI (12) | M263 | # cyber security defences 12 | 0 | 376 | 800 | 350 | 450 | 600 | 800
| KPI (13) | M265 | # cyber security defences 13 | 0 | 0 | 8 | 0 | 2 | 4 | 8
| KPI (14) | M266 | # cyber security defences 14 | 0 | 0 | 8 | 1 | 3 | 5 | 8
4. Streamline compliance | KPI (15) | M267 | # cyber security defences 15 | 0 | 4 | 7 | 3 | 4 | 5 | 7
| KPI (16) | M268 | # cyber security defences 16 | 0 | 0 | 7 | 2 | 3 | 6 | 7
| KPI (17) | M269 | # cyber security defences 17 | 0 | 0 | 2 | 0 | 0 | 0 | 51
| KPI (18) | M270 | # cyber security defences 18 | 0 | 3 | 6 | 3 | 3 | 5 | 6
5. Build Security org/skills | KPI (19) | M271 | # cyber security defences 19 | 0 | 5 | 20 | 5 | 10 | 15 | 20
| KPI (20) | M264 | # cyber security defences 20 | 0 | 0 | 50 | 0 | 15 | 40 | 50
| KPI (21) | M272 | # cyber security defences 21 | 0 | 1 | 6 | 0 | 2 | 4 | 6
| KPI (22) | M273 | # cyber security defences 22 | 0 | 3 | 10 | 3 | 5 | 8 | 10
- confidential -
Export KPIs
Import KPIs

## M252
| Focus Area | Slow down hackers | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M252 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 1
|  | 6 | 2 | 2 | 2 | 1 | 1 | 0 | 2 | 3 | 4 | 6
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 6 | 2 | 2 | 2 | 1 | 1 | 0 | 2 | 3 | 4 | 6

## M253
| Focus Area | Slow down hackers | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M253 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 2
|  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 6
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 6

## M254
| Focus Area | Slow down hackers | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M254 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 3
|  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 20
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 20 | First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.
First progess will be reported in April.

## M255
| Focus Area | Slow down hackers | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M255 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 4
|  | 10000 | 350 | 0 | 0 | 0 | 0 | 0 | 1500 | 4000 | 6000 | 10000
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 10000 | 350 | 0 | 0 | 0 | 0 | 0 | 1500 | 4000 | 6000 | 10000 | First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April
First progress report in CW 13: Pilot and test-users due to productive rollout for AZT shift to April

## M256
| Focus Area | Slow down hackers | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M256 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 5
|  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 5
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 4 | 5

## M257
| Focus Area | Slow down hackers | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M257 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 6
|  | 12 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 4 | 8 | 12
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 12 | 3 | 2 | 2 | 0 | 0 | 0 | 3 | 4 | 8 | 12 | 04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed
04.03. HLD & Requirement documentation completed

## M258
| Focus Area | Slow down hackers | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M258 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 7
|  | 20 | 3 | 2 | 1 | 1 | 1 | 0 | 3 | 6 | 12 | 20
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 20 | 3 | 2 | 1 | 1 | 1 | 0 | 3 | 6 | 12 | 20 | The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished
The finishing of the different documents and getting the approval from the different process owners in many cases can only be archieved after the vendor is determined. This leads to many documents finished at the end of the project.Currently: High Level Design, Procurement and Architcture finished

## M259
| Focus Area | Increase Detection | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M259 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 8
|  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 6
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 6

## M260
| Focus Area | Increase Detection | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M260 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 9
|  | 16 | 6 | 5 | 4 | 1 | 1 | 0 | 5 | 8 | 10 | 16
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 16 | 6 | 5 | 4 | 1 | 1 | 0 | 5 | 8 | 10 | 16

## M261
| Focus Area | Increase Detection | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M261 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 10
|  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 7
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 7 | Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux
Please list the 5 OEs and 2 DCs here: DCs: E1 & E2 OEs: Germany, France, Spain, Ireland,Benelux

## M262
| Focus Area | Increase Detection | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M262 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 11
|  | 40 | 6 | 2 | 1 | 1 | 1 | 0 | 10 | 18 | 28 | 40
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 40 | 6 | 2 | 1 | 1 | 1 | 0 | 10 | 18 | 28 | 40

## M263
| Focus Area | Reduce Damage | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M263 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 12
|  | 800 | 376 | 342 | 307 | 295 | 268 | 0 | 350 | 450 | 600 | 800
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 800 | 376 | 342 | 307 | 295 | 268 | 0 | 350 | 450 | 600 | 800

## M265
| Focus Area | Reduce Damage | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M265 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 13
|  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 8
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 8 | Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack
Three categories: sophisticated attack responses, effectiveness testing of information security solutions, analyzed attack

## M266
| Focus Area | Reduce Damage | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M266 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 14
|  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 5 | 8
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 5 | 8 | First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021
First KPI achievement planned for31 March 2021

## M267
| Focus Area | Streamline compliance | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M267 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 15
|  | 7 | 4 | 1 | 1 | 1 | 1 | 0 | 3 | 4 | 5 | 7
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 7 | 4 | 1 | 1 | 1 | 1 | 0 | 3 | 4 | 5 | 7 | Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded
Artefact #1, #4, #5 and #6 uploaded

## M268
| Focus Area | Streamline compliance | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M268 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 16
|  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 6 | 7
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 6 | 7 | - KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021
- KPI ADO IT Interface implemented and user accepted := 31/05/2021 - KPI ScoreCard implemented and user accepted := 31/05/2021 - KPI Project Risk Assessment BRD signed off := 05/04/2021 - KPI Project Risk Assessment DEV signed off := 12/06/2021 - KPI Cloud Assessment Training Material created := 31/03/2021 - KPI BRD LE compliance reporting signed off := 31/03/2021 - KPI DEV LE compliance reporting signed off := 31/05/2021

## M269
[7 empty] | Focus Area | Streamline compliance | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative | [7 empty] | M269 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 | [7 empty] | # cyber security defences 17
[8 empty] | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51
Board Members | H Ressort | ITC Mapping |  | Group Iso Function | OEs ID | CIM ID | OE | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
Bäte | H1 CEO | 1 | Allianz SE, Allianz Europe | Shared Services | 1 | AZSE | Allianz SE | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 2 | TBD | Asset & Overseas | 2 | AU | Allianz Australia P&C | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
. |  |  |  |  | ∑ | ∑ | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
.
Thallinger | H3 Investments Management | 2 | Allianz Investment | Shared Services | 3 | ADEUS | ADEUS Aktienregister-Service-GmbH | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | Europe 3 | 4 | AGL | Allianz Global Life | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | Shared Services | 5 | AIM | Allianz Investment Management (AIM) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | Shared Services | 6 | ARE | Allianz Real Estate (ARE) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | TBD | 7 | AUL | Allianz Australia Life | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | Shared Services | 8 | IDS | Investment Data Services (IDS) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
. |  |  |  |  | ∑ | ∑ | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6
.
Mascher | H4 Operations | 3 | Allianz Technology | AZ Technology | 9 | AMOS | Allianz Technology | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
. |  |  |  |  | ∑ | ∑ | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
.
Balbinot | H5 Insurance Western & Southern Europe, AZAP | 4 | AZAP | AZAP | 10 | CNPC | Allianz China - P&C | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 11 | CNH | Allianz China - Holding | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 12 | ID | Allianz Indonesia | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 13 | LAPC | Allianz Laos | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 14 | MY | Allianz Malaysia | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 15 | PH | Allianz Philippine - L&H | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 16 | LK | Allianz Sri Lanka | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 17 | AS | Allianz Singapore | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 18 | TWL | Allianz Taiwan - Life | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 19 | TH | Allianz Thailand | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | AZAP | 20 | FIN | FinOS - Holding | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
| H2 Finance, Controlling, Risk | 5 | Allianz Benelux | Europe 2 | 21 | BLX | Allianz Benelux | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk | 6 | Allianz France | Europe 2 | 22 | FR | Allianz France | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk | 7 | Allianz Greece | Europe 3 | 23 | GR | Allianz Greece | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk | 8 | Allianz Italy | Europe 3 | 24 | IT | Allianz Italy | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk | 9 | Allianz Turkey | Europe 3 | 25 | TR | Allianz Turkey | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
. |  |  |  |  | ∑ | ∑ | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16
.
Theis | H7 Insurance German Speaking Countries & CEE | 10 | Allianz Germany | Europe 1 | 26 | AZD | Allianz Germany | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk | 11 | CEE | CEE | 27 | AT | Allianz Austria (Elementar) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | CEE | 28 | BG | Allianz Bulgaria | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | CEE | 29 | CZ | Allianz Czechia | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | CEE | 30 | HU | Allianz Hungary | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | CEE | 31 | HR | Allianz Croatia (Zagreb) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | CEE | 32 | PL | Allianz Poland | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | CEE | 33 | RO | Allianz Romania (Tiriac) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | CEE | 34 | RU | Allianz Russia | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | CEE | 35 | SK | Allianz Slovakia | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  | CEE | 36 | UKR | Allianz Ukraine | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
| H2 Finance, Controlling, Risk | 12 | Allianz Suisse | Europe 1 | 37 | CH | Allianz Switzerland | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
. |  |  |  |  | ∑ | ∑ | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Hunt | H8 Asset Management, USA Life Insurance | 13 | Allianz Asset Management Holding (AAM) | Asset & Overseas | 38 | AAM | Allianz Asset Management Holding (AAM) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| H2 Finance, Controlling, Risk | 15 | Allianz Global Investors (AGI) | Asset & Overseas | 39 | AGI | Allianz Global Investors (AGI) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H2 Finance, Controlling, Risk | 16 | Pacific Invest.Manag. Comp.(PIMCO) | Asset & Overseas | 40 | PIMCO | Pacific Investement Management Company (PIMCO) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H2 Finance, Controlling, Risk | 17 | Allianz Life | Asset & Overseas | 41 | USL | Allianz Life US | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
. |  |  |  |  | ∑ | ∑ | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
.
Peiris | H9 Global Lines & Anglo Markets, MENA, Africa | 18 | Allianz Africa | AZ Africa | 42 | AFR | Allianz Africa | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | AZ Africa | 43 | MA | Allianz Morocco | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | ∑ | ∑ | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
|  | 19 | MENA | MENA | 44 | EGLH | Allianz Egypt L&H | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | MENA | 45 | EGPC | Allianz Egypt P&C | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | MENA | 46 | LB | Allianz Lebanon | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | MENA | 47 | SA | Allianz Saudi Arabia | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | ∑ | ∑ | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  | 20 | Allianz Global Corporate & Specialty (AGCS) | Europe 1 | 48 | AGCS | Allianz Global Corporate & Specialty (AGCS) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 21 | Reinsurance | Europe 1 | 49 | AZRE | Allianz Reinsurance | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 23 | Allianz Ireland | Europe 3 | 50 | IE | Allianz Ireland | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 24 | Allianz UK | Europe 3 | 51 | UK | Allianz UK | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 25 | Euler Hermes Group | Europe 2 | 52 | EH | Euler Hermes | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
. |  |  |  |  | ∑ | ∑ | 11 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
.
de la Sota | H10 Business Transformation | 26 | Allianz Ibero & Latin America | IbertoLatAm | 53 | AR | Allianz Argentina | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | IbertoLatAm | 54 | BR | Allianz Brazil | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | IbertoLatAm | 55 | CO | Allianz Colombia | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | IbertoLatAm | 56 | MX | Allianz Mexico | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | IbertoLatAm | 57 | PT | Allianz Portugal | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  |  | IbertoLatAm | 58 | ES | Allianz Spain (Seguros) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[5 empty] | ∑ | ∑ | 6
|  | 27 | Allianz Partners | Europe 2 | 59 | AWP | Allianz Partners | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  | 28 | TBD | Shared Services | 60 | AZX | AllianzX | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | ∑ | ∑ | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
[7 empty] | 60 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51

## M270
| Focus Area | Streamline compliance | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M270 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 18
|  | 6 | 3 | 3 | 3 | 3 | 1 | 0 | 3 | 3 | 5 | 6
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 6 | 3 | 3 | 3 | 3 | 1 | 0 | 3 | 3 | 5 | 6 | First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021
First milestone (KPI) was reached end of January 2021

## M271
| Focus Area | Build Security org/skills | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M271 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 19
|  | 20 | 5 | 5 | 3 | 1 | 1 | 0 | 5 | 10 | 15 | 20
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 20 | 5 | 5 | 3 | 1 | 1 | 0 | 5 | 10 | 15 | 20

## M264
[7 empty] | Focus Area | Build Security org/skills | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative | [7 empty] | M264 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 | [7 empty] | # cyber security defences 20
[8 empty] | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 40 | 50
Board Members | H Ressort | ITC Mapping |  | Group Iso Function | OEs ID | CIM ID | OE | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
Bäte | H1 CEO | 1 | Allianz SE, Allianz Europe | Shared Services | 1 | AZSE | Allianz SE | [7 empty] | 0
|  | 2 | TBD | Asset & Overseas | 2 | AU | Allianz Australia P&C | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Thallinger | H3 Investments Management | 2 | Allianz Investment | Shared Services | 3 | ADEUS | ADEUS Aktienregister-Service-GmbH | [7 empty] | 0
|  |  |  | Europe 3 | 4 | AGL | Allianz Global Life | [7 empty] | 0
|  |  |  | Shared Services | 5 | AIM | Allianz Investment Management (AIM) | [7 empty] | 0
|  |  |  | Shared Services | 6 | ARE | Allianz Real Estate (ARE) | [7 empty] | 0
|  |  |  | TBD | 7 | AUL | Allianz Australia Life | [7 empty] | 0
|  |  |  | Shared Services | 8 | IDS | Investment Data Services (IDS) | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Mascher | H4 Operations | 3 | Allianz Technology | AZ Technology | 9 | AMOS | Allianz Technology | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Balbinot | H5 Insurance Western & Southern Europe, AZAP | 4 | AZAP | AZAP | 10 | CNPC | Allianz China - P&C | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 11 | CNH | Allianz China - Holding | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 12 | ID | Allianz Indonesia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 13 | LAPC | Allianz Laos | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 14 | MY | Allianz Malaysia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 15 | PH | Allianz Philippine - L&H | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 16 | LK | Allianz Sri Lanka | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 17 | AS | Allianz Singapore | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 18 | TWL | Allianz Taiwan - Life | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 19 | TH | Allianz Thailand | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | AZAP | 20 | FIN | FinOS - Holding | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H2 Finance, Controlling, Risk | 5 | Allianz Benelux | Europe 2 | 21 | BLX | Allianz Benelux | [7 empty] | 0
| H2 Finance, Controlling, Risk | 6 | Allianz France | Europe 2 | 22 | FR | Allianz France | [7 empty] | 0
| H2 Finance, Controlling, Risk | 7 | Allianz Greece | Europe 3 | 23 | GR | Allianz Greece | [7 empty] | 0
| H2 Finance, Controlling, Risk | 8 | Allianz Italy | Europe 3 | 24 | IT | Allianz Italy | [7 empty] | 0
| H2 Finance, Controlling, Risk | 9 | Allianz Turkey | Europe 3 | 25 | TR | Allianz Turkey | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Theis | H7 Insurance German Speaking Countries & CEE | 10 | Allianz Germany | Europe 1 | 26 | AZD | Allianz Germany | [7 empty] | 0
| H2 Finance, Controlling, Risk | 11 | CEE | CEE | 27 | AT | Allianz Austria (Elementar) | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 28 | BG | Allianz Bulgaria | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 29 | CZ | Allianz Czechia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 30 | HU | Allianz Hungary | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 31 | HR | Allianz Croatia (Zagreb) | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 32 | PL | Allianz Poland | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 33 | RO | Allianz Romania (Tiriac) | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 34 | RU | Allianz Russia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 35 | SK | Allianz Slovakia | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  | CEE | 36 | UKR | Allianz Ukraine | [7 empty] | 0
| H2 Finance, Controlling, Risk |  |  |  | ∑ | ∑ | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| H2 Finance, Controlling, Risk | 12 | Allianz Suisse | Europe 1 | 37 | CH | Allianz Switzerland | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
. | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
Hunt | H8 Asset Management, USA Life Insurance | 13 | Allianz Asset Management Holding (AAM) | Asset & Overseas | 38 | AAM | Allianz Asset Management Holding (AAM) | [7 empty] | 0
| H2 Finance, Controlling, Risk | 15 | Allianz Global Investors (AGI) | Asset & Overseas | 39 | AGI | Allianz Global Investors (AGI) | [7 empty] | 0
| H2 Finance, Controlling, Risk | 16 | Pacific Invest.Manag. Comp.(PIMCO) | Asset & Overseas | 40 | PIMCO | Pacific Investement Management Company (PIMCO) | [7 empty] | 0
| H2 Finance, Controlling, Risk | 17 | Allianz Life | Asset & Overseas | 41 | USL | Allianz Life US | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
Peiris | H9 Global Lines & Anglo Markets, MENA, Africa | 18 | Allianz Africa | AZ Africa | 42 | AFR | Allianz Africa | [7 empty] | 0
|  |  |  | AZ Africa | 43 | MA | Allianz Morocco | [7 empty] | 0
[5 empty] | ∑ | ∑ | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 19 | MENA | MENA | 44 | EGLH | Allianz Egypt L&H | [7 empty] | 0
|  |  |  | MENA | 45 | EGPC | Allianz Egypt P&C | [7 empty] | 0
|  |  |  | MENA | 46 | LB | Allianz Lebanon | [7 empty] | 0
|  |  |  | MENA | 47 | SA | Allianz Saudi Arabia | [7 empty] | 0
[5 empty] | ∑ | ∑ | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 20 | Allianz Global Corporate & Specialty (AGCS) | Europe 1 | 48 | AGCS | Allianz Global Corporate & Specialty (AGCS) | [7 empty] | 0
|  | 21 | Reinsurance | Europe 1 | 49 | AZRE | Allianz Reinsurance | [7 empty] | 0
|  | 23 | Allianz Ireland | Europe 3 | 50 | IE | Allianz Ireland | [7 empty] | 0
|  | 24 | Allianz UK | Europe 3 | 51 | UK | Allianz UK | [7 empty] | 0
|  | 25 | Euler Hermes Group | Europe 2 | 52 | EH | Euler Hermes | [7 empty] | 0
. |  |  |  |  | ∑ | ∑ | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
.
de la Sota | H10 Business Transformation | 26 | Allianz Ibero & Latin America | IbertoLatAm | 53 | AR | Allianz Argentina | [7 empty] | 0
|  |  |  | IbertoLatAm | 54 | BR | Allianz Brazil | [7 empty] | 0
|  |  |  | IbertoLatAm | 55 | CO | Allianz Colombia | [7 empty] | 0
|  |  |  | IbertoLatAm | 56 | MX | Allianz Mexico | [7 empty] | 0
|  |  |  | IbertoLatAm | 57 | PT | Allianz Portugal | [7 empty] | 0
|  |  |  | IbertoLatAm | 58 | ES | Allianz Spain (Seguros) | [7 empty] | 0
[5 empty] | ∑ | ∑ | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 27 | Allianz Partners | Europe 2 | 59 | AWP | Allianz Partners | [7 empty] | 0
|  | 28 | TBD | Shared Services | 60 | AZX | AllianzX | [7 empty] | 0
[5 empty] | ∑ | ∑ | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## M272
| Focus Area | Build Security org/skills | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M272 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 21
|  | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 6
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 6 | Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.
Regular weekly touch points are on going. Draft versions of Container final review with patcipants finalied. API Sec. Patterns review is in the final stage only one chapter left. Building Cloud Network Sec. Concept is tested through use cases delivered by AZD and AZP. Overarching Secure Design Principle will be finalized in the upcoming cycle. Enterprise Security Reference Architecture is finalized and now in the pre-final version already shared with AZT ISO and Architect for their initial review.

## M273
| Focus Area | Build Security org/skills | [7 empty] | All yellow marked columns to be filled out
IT Security Initiative |  | M273 | #REF! | [5 empty] | Please fill in your monthly split of planned KPI target values (accumulated plan). Please leave a comment: In which CW will you report your first progress?
Progress KPI Reporting 2021 |  | # cyber security defences 22
|  | 10 | 3 | 3 | 3 | 1 | 1 | 0 | 3 | 5 | 8 | 10
|  | Target 30.06.21 | Actuals 19.03.21 | Actuals 12.03.21 | Actuals 05.03.21 | Actuals 26.02.21 | Actuals 19.02.21 | Baseline 01.01.21 | Plan 03/2021 | Plan 04/2021 | Plan 05/2021 | Plan 06/2021 | Comments
.
|  | 10 | 3 | 3 | 3 | 1 | 1 | 0 | 3 | 5 | 8 | 10 | CW07
CW07
CW07
CW07
CW07
CW07
CW07
CW07
CW07
CW07
CW07
CW07