## 2021_HY1_Measures_master
IT Security Initiative Measures (2021 first half-year)
PMO / Head: Ralf Schneider
PMO / Budget: Marina Dührkop
PMO / Progress Tracking: Julian Steinfeld
as of March 18th, 2021 | [10 empty] | Total HY-1 2021 (k€) | Total HY-1 2021 (k€) | 17297 | - | 5076.6205 | 3064.835 | Progress KPIs
# | Focus Area | MID | PSP Element | Measure name | Measure description / work package | Contract partner | Focus Area Lead | Measure Sponsor | Measure Lead | operating ML (nur bei AZ Technology) | Line Org. Sponsor | Solution Manager | Appr. Budget in k€ (17.12.2020) | Approval Date | Spent in k€ (31.03.2021) | Invoiced in k€ (31.03.2021) | # | Name | Baseline 01.01.2021 | Actuals 05.03.2021 | Actuals 19.03.2021 | Actuals 26.03.2021 | Actuals 02.04.2021 | Actuals 09.04.2021 | Plan 03.2021 | Plan 04.2021 | Plan 05.2021 | Target 30.06..2021 | Status 18.12.2020 | PMO internal status | PMO internal comment | Comments Please contact SecurityInvestmentInitiativeOffice@allianz.com if you would like to receive the current status report of all or individual measures. | Comments PMO | TCB
1 | Slow Down Hackers | M252 | AZSE-H4-800225 | Cyber super defence 1 | Measure description / work package 1 | Meta | Focus Area Lead 1 | Measure Sponsor 1 | Measure Lead 1 | --- | Line Org. Sponsor 1 | Solution Manager 1 | 2500 | 26.11.2020 / 14.12.2020 | 295.515 | 153.8031 | KPI (1) | # cyber scurity defences 1 | 0 | 2 | 2 | 2 | 2 |  | 2 | 3 | 4 | 6 |  |  |  |  | * Email an Huber/Schnier/Willis/Feser
2 | Slow Down Hackers | M253 | AZSE-H4-800226 | Cyber super defence 2 | Measure description / work package 2 | AZT SecOps | Focus Area Lead 2 | Measure Sponsor 2 | Measure Lead 2 | operating ML (nur bei AZ Technology) 2 | Line Org. Sponsor 2 | Solution Manager 2 | 500 | 26.11.2020 | 211.2501 | 211.2501 | KPI (2) | # cyber scurity defences 2 | 0 | 0 | 0 | 1 | 1 |  | 1 | 2 | 3 | 6
3 | Slow Down Hackers | M254 | AZSE-H4-800227 | Cyber super defence 3 | Measure description / work package 3 | Meta | Focus Area Lead 3 | Measure Sponsor 3 | Measure Lead 3 | tbd | Line Org. Sponsor 3 | Solution Manager 3 | 850 | 26.11.2020 | 313.5625 | 100.1787 | KPI (3) | # cyber scurity defences 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 10 | 20 | 20
4 | Slow Down Hackers | M255 | AZSE-H4-800228 | Cyber super defence 4 | Measure description / work package 4 | AZT SecOps | Focus Area Lead 4 | Measure Sponsor 4 | Measure Lead 4 | operating ML (nur bei AZ Technology) 4 | Line Org. Sponsor 4 | Solution Manager 4 | 990 | 14.12.2020 | 234.9574 | 232.2454 | KPI (4) | # cyber scurity defences 4 | 0 | 0 | 350 | 350 | 500 |  | 1500 | 4000 | 6000 | 10000 |  |  |  |  | * monthly progress meeting aufsetzen (mid march) * Rollout ab März
5 | Slow Down Hackers | M256 | AZSE-H4-800229 | Cyber super defence 5 | Measure description / work package 5 | AZT SecOps | Focus Area Lead 5 | Measure Sponsor 5 | Measure Lead 5 | --- | Line Org. Sponsor 5 | Solution Manager 5 | 300 | 26.11.2020 | 7.8359 | 10.99 | KPI (5) | # cyber scurity defences 5 | 0 | 0 | 0 | 0 | 1 |  | 1 | 2 | 4 | 5
6 | Slow Down Hackers | M257 | AZSE-H4-800230 | Cyber super defence 6 | Measure description / work package 6 | AZT SecOps | Focus Area Lead 6 | Measure Sponsor 6 | Measure Lead 6 | --- | Line Org. Sponsor 6 | Solution Manager 6 | 1050 | 26.11.2020 | 264.2542 | 260.677 | KPI (6) | # cyber scurity defences 6 | 0 | 2 | 3 | 3 | 3 |  | 3 | 4 | 8 | 12 |  |  |  |  | * monthly progress meeting (mid of March) --> 2 KPIs?
7 | Slow Down Hackers | M258 | AZSE-H4-800231 | Cyber super defence 7 | Measure description / work package 7 | AZT SecOps | Focus Area Lead 7 | Measure Sponsor 7 | Measure Lead 7 | operating ML (nur bei AZ Technology) 7 | Line Org. Sponsor 7 | Solution Manager 7 | 800 | 14.12.2020 | 106.5091 | 109.3991 | KPI (7) | # cyber scurity defences 7 | 0 | 1 | 3 | 3 | 3 |  | 3 | 6 | 12 | 20 |  |  |  |  | * RS fragen, ob progress Meeting (eher nicht, da Ende Feb vorbei) --> keine Serie
8 | Increase Detection | M259 | AZSE-H4-800232 | Cyber super defence 8 | Measure description / work package 8 | AZT SecOps | Focus Area Lead 8 | Measure Sponsor 8 | Measure Lead 8 | operating ML (nur bei AZ Technology) 8 | Line Org. Sponsor 8 | Solution Manager 8 | 720 | 14.12.2020 | 117.6249 | 117.6249 | KPI (8) | # cyber scurity defences 8 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2 | 4 | 6 |  |  |  |  | * monthly progress meeting aufsetzen (mid march)
9 | Increase Detection | M260 | AZSE-H4-800233 | Cyber super defence 9 | Measure description / work package 9 | AZT SecOps | Focus Area Lead 9 | Measure Sponsor 9 | Measure Lead 9 | operating ML (nur bei AZ Technology) 9 | Line Org. Sponsor 9 | Solution Manager 9 | 835 | 14.12.2020 | 135.4709 | 82.0738 | KPI (9) | # cyber scurity defences 9 | 0 | 4 | 6 | 6 | 10 |  | 5 | 8 | 10 | 16 |  |  |  |  | * monthly progress meeting aufsetzen (mid march) - auch Huber, Schnier einladen
10 | Increase Detection | M261 | AZSE-H4-800234 | Cyber super defence 10 | Measure description / work package 10 | AZT SecOps | Focus Area Lead 10 | Measure Sponsor 10 | Measure Lead 10 | operating ML (nur bei AZ Technology) 10 | Line Org. Sponsor 10 | Solution Manager 10 | 1780 | 26.11.2020 | 473.2184 | 431.1213 | KPI (10) | # cyber scurity defences 10 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2 | 5 | 7 |  |  |  |  | * Progress Meeting 15 min
11 | Increase Detection | M262 | AZSE-H4-800235 | Cyber super defence 11 | Measure description / work package 11 | AZT SecOps | Focus Area Lead 11 | Measure Sponsor 11 | Measure Lead 11 | operating ML (nur bei AZ Technology) 11 | Line Org. Sponsor 11 | Solution Manager 11 | 900 | 26.11.2020 | 242.1709 | 221.3069 | KPI (11) | # cyber scurity defences 11 | 0 | 1 | 6 | 13 | 14 |  | 10 | 18 | 28 | 40 |  |  |  |  | * monthly progress meeting aufsetzen (mid march) - auch Huber, Schnier einladen
12 | Reduce Damage | M263 | AZSE-H4-800236 | Cyber super defence 12 | Measure description / work package 12 | AZT SecOps | Focus Area Lead 12 | Measure Sponsor 12 | Measure Lead 12 | operating ML (nur bei AZ Technology) 12 | Line Org. Sponsor 12 | Solution Manager 12 | 730 | 14.12.2020 | 204.0281 | 204.0281 | KPI (12) | # cyber scurity defences 12 | 0 | 307 | 376 | 378 | 402 |  | 350 | 450 | 600 | 800 |  |  |  |  | * Progress Meeting 15 min
13 | Reduce Damage | M265 | AZSE-H4-800238 | Cyber super defence 13 | Measure description / work package 13 | Meta | Focus Area Lead 13 | Measure Sponsor 13 | Measure Lead 13 | --- | Line Org. Sponsor 13 | Solution Manager 13 | 500 | 14.12.2020 | 443.105 | 1.35 | KPI (13) | # cyber scurity defences 13 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2 | 4 | 8 |  |  |  |  | 2 runter gegangen (10 ist ok)
14 | Reduce Damage | M266 | AZSE-H4-800239 | Cyber super defence 14 | Measure description / work package 14 | Meta | Focus Area Lead 14 | Measure Sponsor 14 | Measure Lead 14 | --- | Line Org. Sponsor 14 | Solution Manager 14 | 300 | 17.12.2020 | 103.7781 | 19.9281 | KPI (14) | # cyber scurity defences 14 | 0 | 0 | 0 | 0 | 1 |  | 1 | 3 | 5 | 8
15 | Streamline Compliance | M267 | AZSE-H4-800240 | Cyber super defence 15 | Measure description / work package 15 | AZT Ruttkowski | Focus Area Lead 15 | Measure Sponsor 15 | Measure Lead 15 | --- | Line Org. Sponsor 15 | Solution Manager 15 | 650 | 14.12.2020 | 372.3266 | 242.9435 | KPI (15) | # cyber scurity defences 15 | 0 | 1 | 4 | 4 | 4 |  | 3 | 4 | 5 | 7
16 | Streamline Compliance | M268 | AZSE-H4-800241 | Cyber super defence 16 | Measure description / work package 16 | Meta | Focus Area Lead 16 | Measure Sponsor 16 | Measure Lead 16 | --- | Line Org. Sponsor 16 | Solution Manager 16 | 965 | 14.12.2020 | 444.1597 | 244.4141 | KPI (16) | # cyber scurity defences 16 | 0 | 0 | 0 | 0 | 0 |  | 2 | 3 | 6 | 7
17 | Streamline Compliance | M269 | AZSE-H4-800242 | Cyber super defence 17 | Measure description / work package 17 | AZT - Fabian Topp | Focus Area Lead 17 | Measure Sponsor 17 | Measure Lead 17 | --- | Line Org. Sponsor 17 | Solution Manager 17 | 315 | 14.12.2020 | 47.056 | 0 | KPI (17) | # cyber scurity defences 17 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 50
18 | Streamline Compliance | M270 | AZSE-H4-800243 | Cyber super defence 18 | Measure description / work package 18 | Meta | Focus Area Lead 18 | Measure Sponsor 18 | Measure Lead 18 | --- | Line Org. Sponsor 18 | Solution Manager 18 | 612 | 17.12.2020 | 209.6425 | 112.5812 | KPI (18) | # cyber scurity defences 18 | 0 | 3 | 3 | 3 | 3 |  | 3 | 3 | 5 | 6
19 | Build Security Organization / Skills | M271 | AZSE-H4-800244 | Cyber super defence 19 | Measure description / work package 19 | AZT SecOps | Focus Area Lead 19 | Measure Sponsor 19 | Measure Lead 19 | operating ML (nur bei AZ Technology) 19 | Line Org. Sponsor 19 | Solution Manager 19 | 635 | 17.12.2020 | 95.886 | 95.886 | KPI (19) | # cyber scurity defences 19 | 0 | 3 | 5 | 5 | 6 |  | 5 | 10 | 15 | 20 |  |  |  |  | * monthly progress meeting aufsetzen (mid march) - auch Huber, Schnier einladen
20 | Build Security Organization / Skills | M264 |  | Cyber super defence 20 | Measure description / work package 20 | Meta | Focus Area Lead 20 | Measure Sponsor 20 | Measure Lead 20 | --- | Line Org. Sponsor 20 | Solution Manager 20 | 125 |  | 46.0206 | 20.9281 | KPI (20) | # cyber scurity defences 20 | 0 | 0 | 0 | 0 | 0 |  | 0 | 15 | 40 | 50
21 | Build Security Organization / Skills | M272 | AZSE-H4-800245 | Cyber super defence 21 | Measure description / work package 21 | EY /Meta (305/15) | Focus Area Lead 21 | Measure Sponsor 21 | Measure Lead 21 | --- | Line Org. Sponsor 21 | Solution Manager 21 | 320 | 17.12.2020 | 161.1009 | 2.75 | KPI (21) | # cyber scurity defences 21 | 0 | 0 | 1 | 1 | 1 |  | 0 | 2 | 4 | 6 |  |  |  |  | * List of documents
22 | Build Security Organization / Skills | M273 | AZSE-H4-800246 | Cyber super defence 22 | Measure description / work package 22 | Meta | Focus Area Lead 22 | Measure Sponsor 22 | Measure Lead 22 | --- | Line Org. Sponsor 22 | Solution Manager 22 | 500 | 17.12.2020 | 382.6572 | 118.6309 | KPI (22) | # cyber scurity defences 22 | 0 | 3 | 3 | 3 | 3 |  | 3 | 5 | 8 | 10 |  |  |  |  | * list of trainng products
23 | PMO | M251 | AZSE-H4-800179 | Cyber super defence 23 | Measure description / work package 23 | Meta | Focus Area Lead 23 | Measure Sponsor 23 | Measure Lead 23 | --- | Line Org. Sponsor 23 | Solution Manager 23 | 420 | 17.12.2020 | 164.4905 | 70.7244
* A list of services, documents, milestones, components or trainings is documented and can be provided by PMO on demand ** Budget increase according to TCB approval on 18.03.2021 for M255 (€140k ) and M258 (€600k)
**
**

## Contacts_Measure Lead & Deputy
IT Security Initiative Measures (2020 second half-year) | IT Security Initiative Measures (2020 second half-year)
PMO / Head: Ralf Schneider
PMO / Budget: Marina Dührkop
PMO / Progress Tracking: Julian Steinfeld
as of September 4th, 2020 |  |  | Total HY-2 2020 (k€)
# | Focus Area | MID | Measure name | Measure Sponsor | Measure Lead | Deputy Measure Lead | Number | Email
1 | Slow Down Hackers | M252 | Cyber super defence 1 | Measure Sponsor 1 | Measure Lead 1 | Deputy Measure Lead 1 | 4915212345 | firstname.lastname1@allianz.com
2 | Slow Down Hackers | M253 | Cyber super defence 2 | Measure Sponsor 2 | Measure Lead 2 | Deputy Measure Lead 2 | 4915212346 | firstname.lastname1@allianz.com
3 | Slow Down Hackers | M254 | Cyber super defence 3 | Measure Sponsor 3 | Measure Lead 3 | Deputy Measure Lead 3 | 4915212347 | firstname.lastname1@allianz.com
4 | Slow Down Hackers | M255 | Cyber super defence 4 | Measure Sponsor 4 | Measure Lead 4 | Deputy Measure Lead 4 | 4915212348 | firstname.lastname1@allianz.com
5 | Slow Down Hackers | M256 | Cyber super defence 5 | Measure Sponsor 5 | Measure Lead 5 | Deputy Measure Lead 5 | 4915212349 | firstname.lastname1@allianz.com
6 | Slow Down Hackers | M257 | Cyber super defence 6 | Measure Sponsor 6 | Measure Lead 6 | Deputy Measure Lead 6 | 4915212350 | firstname.lastname1@allianz.com
7 | Slow Down Hackers | M258 | Cyber super defence 7 | Measure Sponsor 7 | Measure Lead 7 | Deputy Measure Lead 7 | 4915212351 | firstname.lastname1@allianz.com
8 | Increase Detection | M259 | Cyber super defence 8 | Measure Sponsor 8 | Measure Lead 8 | Deputy Measure Lead 8 | 4915212352 | firstname.lastname1@allianz.com
9 | Increase Detection | M260 | Cyber super defence 9 | Measure Sponsor 9 | Measure Lead 9 | Deputy Measure Lead 9 | 4915212353 | firstname.lastname1@allianz.com
10 | Increase Detection | M261 | Cyber super defence 10 | Measure Sponsor 10 | Measure Lead 10 | Deputy Measure Lead 10 | 4915212354 | firstname.lastname1@allianz.com
11 | Increase Detection | M262 | Cyber super defence 11 | Measure Sponsor 11 | Measure Lead 11 | Deputy Measure Lead 11 | 4915212355 | firstname.lastname1@allianz.com
12 | Reduce Damage | M263 | Cyber super defence 12 | Measure Sponsor 12 | Measure Lead 12 | Deputy Measure Lead 12 | 4915212356 | firstname.lastname1@allianz.com
13 | Reduce Damage | M265 | Cyber super defence 13 | Measure Sponsor 13 | Measure Lead 13 | Deputy Measure Lead 13 | 4915212357 | firstname.lastname1@allianz.com
14 | Reduce Damage | M266 | Cyber super defence 14 | Measure Sponsor 14 | Measure Lead 14 | Deputy Measure Lead 14 | 4915212358 | firstname.lastname1@allianz.com
15 | Streamline Compliance | M267 | Cyber super defence 15 | Measure Sponsor 15 | Measure Lead 15 | Deputy Measure Lead 15 | 4915212359 | firstname.lastname1@allianz.com
16 | Streamline Compliance | M268 | Cyber super defence 16 | Measure Sponsor 16 | Measure Lead 16 | Deputy Measure Lead 16 | 4915212360 | firstname.lastname1@allianz.com
17 | Streamline Compliance | M269 | Cyber super defence 17 | Measure Sponsor 17 | Measure Lead 17 | Deputy Measure Lead 17 | 4915212361 | firstname.lastname1@allianz.com
18 | Streamline Compliance | M270 | Cyber super defence 18 | Measure Sponsor 18 | Measure Lead 18 | Deputy Measure Lead 18 | 4915212362 | firstname.lastname1@allianz.com
19 | Build Security Organization / Skills | M271 | Cyber super defence 19 | Measure Sponsor 19 | Measure Lead 19 | Deputy Measure Lead 19 | 4915212363 | firstname.lastname1@allianz.com
20 | Build Security Organization / Skills | M264 | Cyber super defence 20 | Measure Sponsor 20 | Measure Lead 20 | Deputy Measure Lead 20 | 4915212364 | firstname.lastname1@allianz.com
21 | Build Security Organization / Skills | M272 | Cyber super defence 21 | Measure Sponsor 21 | Measure Lead 21 | Deputy Measure Lead 21 | 4915212365 | firstname.lastname1@allianz.com
22 | Build Security Organization / Skills | M273 | Cyber super defence 22 | Measure Sponsor 22 | Measure Lead 22 | Deputy Measure Lead 22 | 4915212366 | firstname.lastname1@allianz.com
23 | PMO | M251 | IT Security Initiative Hub